## Template for institutions
| HREiR Action plan (2023-2026) | [6 empty] | Add institutional logo
Details
| Institution name: | De Montfort University |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | 17 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 2023-01-27 |  |  |  | Research staff |  | 17 | Figure as of 31 December 2022
| Institutional context: | The main beneficiaries are academics whose workload include research. This includes those on research and teaching contracts, as well as research staff (those on fixed term contracts). |  |  |  | Postgraduate researchers
[6 empty] | Research and teaching staff |  | 988 | Figure as of 31 December 2022
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat. | Work with HR so that line managers of academic staff are made aware of the Concordat principles; embed Concordat in faculty (FRIC) and university (URBIC) research and enterprise committee discussions Raise awareness of Concordat, particularly in PI training and on flagship programmes like the Future Research Leaders programme | Yes | Sept-2025 Oct-2026 | RSD; HR; PVCR, APVCR, ADRs; Theme Directors | Increase of academic staff awareness of Researcher Development Concordat in future surveys to 60% (40% unaware) 50% of Principal Investigators and Future Research Leaders demonstrate awareness of their obligations and responsibilities in managing research staff or other researchers in future survey. | Measuring awareness of PIs and Future Research Leaders is a new metric as such no gap analysis in relation to this figure from the 2021-2023 action plan.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | Institutional policies and practices to continue to have ‘Equality Impact Assessments’ done to ensure no population by protected characteristics or career stage is disproportionately negatively affected. Ensure that institutional policies / practices relevant to research(ers) are subject to periodic review (at least once every 3 years) Collect feedback on promotions applications Ensure institutional policies/practices relevant to researchers are highlighted in the central induction process led by POD, and the faculty inductions. | Yes | Sept-2025 Sept-2025 Sept-2025 Oct-2023 | EDI Team; RSD | Review of EIAs conducted on institutional policies and practices to see projected and actual effects on researcher populations. Standing item on research-related committees to review policies and maintain a log of changes/updates to these. Increase awareness of institutional policies and practices by 20% from 25%. | The 2022 Research Environment and Culture survey measured awareness against research related policies only.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Collate data from University-wide survey and Faculty-based initiatives to collect feedback for improvements from researchers Continue to provide opportunities for staff to feed back on emerging strategies and policies (e.g. focus groups, Green Paper) Ensure that Race Equality and Athena SWAN survey results are disaggregated by research roles where possible. | Yes | November 2025 March 2023 March 2024 | RSD; PVCR; ADRs | Increase value and opportunity scores by 10% across all categories (e.g. sufficient time; opportunities to attend conferences; decision making and such) measured in the Research Environment and Culture Survey. Current scores average to around 25%. Report a10% increase of positive free-text statements linked to the question on 'how would you describe DMU's Research Environment and Culture'. Currently 46% comments are critical but 42% chose not to respond in the free text. Communication to staff (e.g. ‘you said we did’ type comms on how researcher views are being considered and action taken. Intersectional understanding and corresponding responses are developed.
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Regular faculty-based events with follow-up informal networks, particularly for ECRs and new researchers following staff induction. Conduct a review existing mentoring practices across all faculties and institutes Develop resources for research mentors and research mentees Institute- and theme-led support across career stages with appropriate buddying and mentoring | No | September 2023 October 2024 January 2024 | ADRs and HR RSD; ADRs ADRs and POD | Staff feel better connected with other researchers and DMU research culture. Staff feel collegiality and support to colleagues is valued by the institution measured by internal survey. Increase value scores by 10% (in line with impact noted above), in particular those linked to peer review, mentoring and management and administration. Enhanced visibility for research and researchers, particularly at ECR stage, where they are recognised for their contributions and supported to progress.
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | Ensure research time allocated and recognised in work-loading process Schedule training and research opportunities within appropriate times. | Yes | October 2023 | Deans/Heads of School; RSD; ADRs | Academic staff able to use time to conduct research and fufilil objectives. Currently academic staff indicate they need to use time outside of workload to conduct research - next survey the aim is to decrease the comments linked to non-workloaded research. Staff able to realise time allocated for research/ scholarship. Good practice sharing sessions on ensuring wellbeing of staff with positive feedback. Programme of training shows scheduling aligns with guidance on doing activities duringlargely confined within core work hours.
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | Develop and deliver training for managers of researchers with focus on managing workloads as a means to support wellbeing and mental health within staff | Yes | January 2024 | RSD in collaboration with ADRs | Delivery of workshops and positive feedback from sessions.
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health.
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers.
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health.
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | Develop resources on how to recognise micro aggression/bullying etc. Communicate new resource on how to report managers' discrimination, bullying and harassment. HR policies provided at at staff induction Training on how to recognise micro aggression/bullying etc. Embed research as a positive activity across all academic work Culture and environment where research and researchers are supported | Yes | October 2023 January 2024 January 2025 | POD | Increase confidence and transparency in reporting. Also in Code of Conduct for Staff and Governors. Between 1-5 cases reported. Research as a positive activity and contributing to University culture will see an increase by13% (currently 7% of respondents in our Research Culture and Environment survey agreed that DMU had a positive environment).This would see 20% overall positive responses in the next such survey. | Reporting on number of cases is a new measure and thus no baseline is available.
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying.
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | All managers to complete mandatory EDI training, including ‘Understanding Bias’. Completion rates to be monitored annually. All managers to undertake anti-racist training. | No | Nov 2023 Nov 2024 | ADRs; POD EDI Team | 80% of line managers of research staff to have completed the Equality Diversity Essentials (EDE) training; increase Unconscous Bias Training completed by line managers of research staff by 30% (currently at 6%). | Anti-racist training is a new initiative to be launched in 2024.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | All researchers to complete mandatory EDI training, including ‘Understanding Bias’. Completion rates to be monitored | No | Nov 2023 | ADRs; POD | Increase overall completions of mandatory training by 10% (currently at 60% for EDE training and 50% for Unconscious Bias training). Grant application statements on EDI not generic but providing specific context and examples, whilst adhering to employer and funder policies.
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | Research-related workshops and events to cover research integrity – embed in grants or other workshops. Funder visits briefed to encourage conversation on integrity. Staff Induction to embed research integrity within its format. | No | Sept 2025 | RSD; ADRs; Faculty Deans; POD | 15% of staff indicated 'nearly full knowledge' of the Concordat to Support Research Integrity in the 2022 Research Environment and Culture Survey. Increase this value by 15% in 3 years. Increase uptake of engagement with Research Integrity training, including asynchronous e-modules by 20% (currently uptake of e-modules is very low).
ECM3 | Ensure managers report and address incidents of poor research integrity.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct.
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | Researchers at all career stages – early to professoriate – represented on key research-related committees at faculty and university-level. Researchers at all career stages provided opportunities to feed into policy consultations (e.g. Green Paper on research) | Yes | Sept 2023 | ADRs; PVCR; APVCR | Representation on core committee membership – FRICs, URIC, UREC, RDC EDI analysis of policies to be implemented consider impacts on different career stages.Focus groups or other mechanisms seeking feedback on institutional research-related policies provide career-stage based opportunities to do this.
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution.
EM5 | Engage with opportunities to contribute to relevant policy development within their institution.
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution.
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | Career stage-related training pathways for ECRs and MCRs, with MCRs supporting ECRs, encouraging researchers to see their role as key stakeholders Research-related activties such as peer reviewing, mentoring, and supervision recognised institutionally via internal communications and promotions criteria, embedded, supported and delivered through new institute structures. | No | Sept 2023 | RSD POD | Increase in ECR and MCR researcher engagement measured across all strands of researcher development activity by 15% (currently at 30%). Value scores linked to contributions to institutional research-related activities to increase by 10%. | Researcher development activities are managed by Research Services; The data does not include faculty/research institute activities.
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | Raise awareness around the ‘responsible use of metrics’ strand of activity to ensure fair and inclusive selection and appointment practices Pilot use of R4RI (new format of narrative CV that UKRI is piloting at the moment) in recruitment processes. | Yes | June 2024 | POD; RSD; Responsible Metrics Champions | Advertisements of posts steering clear of the use of H-indices or other metrics Uptake of opportunity to provide narrative CVs for academic job opportunities at DMU Feedback on the benefits of this CV | This is a new endeavour and thus no baseline figures are available.
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | Continue with research induction emails as a quick way to share key resources and policy information; Reformat staff induction to include Research as a core part of University business. Organise and host faculty-based events to encourage community building for researchers | Yes | January 2023 March 2023 September 2023 | RSD POD ADRs | 100% of new researchers sent an induction email within 1 month of starting Research activity and successes included and celebrated at staff induction; POD to report on feedback on the inclusion of this in new staff induction. 5 faculty-level events per year with 20% engagement from academics. Institute level mentoring and engagement with all research-active staff at early and mid career stages, with senior staff, including professoriate, leading good practice sharing. | Faculty-based events are currently not captured centrally; part of this action will include mechanisms to capture faculty-level engagement data starting in September.
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | Relaunch of the promotions criteria to make clear the way staff can work towards promotion and progression and the role of research in this. Redevelopment of reward and recognition system so that staff are recognised for their work across the institution and not just within institutes and schools. | Yes | March 2023 | PVCR; POD; ADRs | Establishment of revised clear criteria Positive survey responses on reward and recognition at DMU and increase in positive opportunity scores from 18% to 40%.
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers.
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding.
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder.
ER2 | Researchers understand their reporting obligations and responsibilities.
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | Review appraisal engagement with aim to make appraisals less an ‘annual’ activity but a continual and ongoing activity Develop guidance for mentors of researchers on how to lead discussions on career progression and encourage their mentees to take up opportunities Training to be developed in POD for line management - notably for new line managers | Yes | Sept 2025 Sept 2024 Sept 2025 | POD | Internal survey feedback from researchers on how supported in their roles they are from line managers. Currently 53.4% of staff indicate their line managers are supportive of professional development - actions should see an increase of this to 60%. Line managers feel they have adequate training assessed through feedback and internal surveys. | The internal survey will be adjusted to allow for analysis of line manager responses. The 2022 survey did not include this field.
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | Actions linked to EI3, EI4 demonstrates our commitment to EI5. PODs reward and recognition scheme to include item linked to people management. | Yes | Sept 2025 | POD | A fit-for-purpose appraisal system that supports people at all career stages. Improved engagement with appraisal system Line managers feel they have adequate training assessed through feedback and internal surveys.
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care.
EM4 | Managers actively engage in regular constructive performance management with their researchers.
ER3 | Researchers positively engage with performance management discussions and reviews with their managers.
Job security
The aim of this obligation is to improve the job security of researchers.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress.
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | Circulate regular bulletin on opportunities to engage in professional development opportunities including talks about research being done in a range of employment sectors. | Yes | Sept 2023 | RSD | 25% increase of post-doctoral research staff engaging in professional development activities, including training, sandpits and other events that support research careers. Retention of research-active staff from 2023/24 | Data from 2021-2023 showed 37 bookings across the 2 years shared between the 12-18 research staff (note - at the start of 2021, there were 12 research staff; at the time of the report this number increase to 18). The goal would be to increase engagement but also to improve data capture in relation to research staff.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities.
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development.
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year.
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews.
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually.
PCDR4 | Researchers positively engage in career development reviews with their managers.
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | Communicate to Research Staff on FT and their line managers contracts quarterlyto be contacted quarterly to ensure they are aware of extra support around professional development advise offered from Research Services/Researcher Development Research Development Managers ensure PIs or researchers applying for funds linked to the creation of a Fixed Term research post are made aware of this service | Yes | January 2024 | RSD | 100% of research staff sent emails regarding the extra support for them; line managers also made aware Engagement of Research Staff with Researcher Development activities
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications.
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | Create/extend dedicated programmes to support different career stages, promote interdisciplinary activity and secure time for research. | Yes | October 2024 | PVCR; APVCR; ADRs; RSD | Numbers awarded sabbaticals Only 18% of academics indicated they had sufficient time to develop research profile and leadership; these actions aim to increase the figure to 30%.
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours.
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development.
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this.
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments.
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments.
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 |  |  |  |  | ADR | Associate Deans of Research
2 |  |  |  |  | APVCR | Associate Pro Vice-Chancellor for Research
3 |  |  |  |  | DMU | De Monfort University
4 |  |  |  |  | EDE | Equality Diversity Essentials
5 |  |  |  |  | EDI | Equality, Diversity and Inclusion
6 |  |  |  |  | HR | Human Resources
7 |  |  |  |  | PI | Principal Investigator
8 |  |  |  |  | POD | People and Organisational Development
9 |  |  |  |  | PVCR | Pro Vice-Chancellor for Research
10 |  |  |  |  | RSD | Research Services Directorate
11 |  |  |  |  | TDs | Theme Directors
12
13
14
15
16
17
18
19
20

## Funders' obligations
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions
Employment
Job security
The aims of these obligation are to improve the job security of early career researchers.
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to do so.
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Guidance
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: | Enter relevant information |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | Enter relevant information |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | Enter relevant information |  |  |  | Research staff |  |  | These are your primary beneficiaries, and should be prioritised across the action plan - both by being targeted with actions and evaluated through success measures.
| Institutional context: | Enter relevant information that helps frame the action plan and the intended institutional audience. For example, this box can be used to disclose the research intensiveness of the institution, providing a justification for the breadth/depth of the actions disclosed. |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Describe here your actions/interventions for meeting the obligation, referring to actions elsewhere in the action plan if preferred. | Has the action been carried forward from a previous action plan? "yes" / "no" | Indicate a month and year | Name all key parties responsible for the action(s) and success measure(s) | Describe here your success measure(s), used to report against the intended impact for researchers and incorporating researchers' views wherever possible. | Describe here any supplementary information. | Describe here a written summary of the progress made against the obligation, taking a broad view of the people and/or organisational development that may have occurred. | Provide evidence that directly reports against all success measures described previously. | Indicate the next steps for the action from the following options: "ongoing" (if the deadline is scheduled in the future), "carried forward" (if the action was not completed as planned by the initial deadline) or "no further action" (accompanied by a brief explanation).
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | Institutions planning actions for specific funders' obligations can insert these obligations into the relevant section of the institution template.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | Use these spaces to provide links and references for information provided in the action plan. |  |  |  |  | Use these spaces to describe abbreviations and
2 | [5 empty] | terms used in the action plan.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
N.B. This section is for reporting only, and should not be completed prior to the beginning of the action plan's term.
For brevity, the remaining obligations have been omitted from this 'Guidance' sheet.

## Tips
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff |  |  | Only include institutional audiences considered to directly benefit from the action plan, remembering that research staff should be prioritised.
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers. Our internal evaluation revealed that researchers feel the university strategic priorities do not reflect their own (62% in a consultation said that they felt disconnected from the university's recent 'Strategy 2030'). Heads of Faculties also report from conversations at committee meetings that researchers feel the university's strategic priorities are not entirely aligned with the reality felt in specific research disciplines. Optional: Institutions can use this space (if desired) to discuss the context that frames the actions and success measures disclosed.
ECI1 | Ensure all relevant staff are aware of the Concordat
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | Providing actions for every obligation is not mandatory, although action plans should aim to target those in their priority areas and/or those highlighted by researchers during the internal evaluation.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Host programme of Faculty- and institution-wide workshops on research culture, capturing local and broader views on key themes in research and reflecting these with the institution's 'Strategy 2030' priorities. Gather a comprehensive range of anonymous views from research staff on how they feel their Faculty research environment compares to the institution as a whole through quarterly Faculty pulse surveys. | no yes | Jul-23 Being specific (rather than only stating "ongoing" or "annually") indicates that reporting has been properly scheduled and that actions are timebound. May-23 | • RCWG • Heads of Faculties • PVC-RI • Faculty-HR • RCWG Broad and specific responsibility can show a joined-up approach to working, connects institutional stakeholders around the Researcher Development Concordat and also shares the workload. | • Host quarterly workshops for each Faculty, and biannual institutional workshops. Success measures like this (i.e., "action completed") are acceptable but should be complemented by other measures that show the impact of the action. • Drafting of workshop reports led by research staff attendees, and reports instated as a standing agenda item at Faculty committee meetings. • At least 30 research staff attendance (on average) at Faculty workshops. Positive post-event feedback from at least 80% of research staff attendees. • At least 40% of research staff (on average) across all 5 Faculties respond to Faculty pulse surveys. Success measures like these allow institutions to qualitatively and quantitatively assess progress against the obligation. Note the words underlined in the obligation and consider how the success measures could align with these. Setting numerical (i.e., SMART) targets can provide an unambiguous benchmark to report progress against in the future. |  | Programme of workshops conducted digitally due to ongoing COVID restrictions (1). Attendance was encouraging, with a good number of research staff joining and contributing to both discussions and the chat function. Research staff were less engaged in the reporting of the workshops than hoped, partially attributed to the less stimulating setting of online events. Feedback from research staff attendees was very positive, and both this feedback and the workshop discussion points were fed into Faculty committee meetings. In one instance, this prompted a Head of Faculty to set up focus groups to explore one particular issue more closely. Faculty pulse survey engagement was encouraging, albeit variable across the Faculties. The findings and trends will help inform future Concordat action plans and the university's Research Culture manifesto. By describing the action's progress in narrative form, institutions can explain success in greater detail, or mitigate challenges experienced, by providing helpful contextual information. | • All 5 Faculties' workshops held quarterly, as well as two workshops held at an institutional level. • Workshop reporting only partially led by research staff across the Faculties. All Faculty committees successfully instated research culture reports as an agenda item. • 34 research staff attended each workshop on average. 86% of research staff attendees gave positive post-event feedback, with 84% saying they "found the workshop to be helpful". • 38±3% of research staff responded to pulse surveys across all Faculties, although some only received 35% research staff response rates. Ensuring you report against all success measures provides a better assessment of the impact achieved and shows commitment to researchers that the institution cares about their views and behaviour. | no further action (action now considered normal business) After selecting from one of the set responses in the column header, institutions can briefly indicate the rationale for this decision (e.g., "action successfully embedded" or "action delayed, partially completed").
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Even if no action is intended/needed, it is encouraged to include success measures that show how different stakeholders engage with/benefit from other actions. |  | Jul-23 | • RCWG | At least 70% of research staff answering CEDARS q42.4 ("feel included in your immediate research environment/group") agree or strongly agree (CEDARS 2021: 62%) | Survey response rate in 2021: 16% research staff (n=147) Optional: This space can be used to provide details not suitable for the other columns. For example, you can add information relevant to an action and/or a success measure to help demonstrate feasibility. | CEDARS response rate improved considerably after a campaign of targeted communications. This coincided with less positive responses for q42.4 than anticipated, suggesting that the university is now successfully reaching a previously 'silent' yet dissatisfied group of research staff with the survey. | 64% of research staff responded agree/strongly agree for CEDARS q42.4. 22% of all research staff (n=202) responded to CEDARS.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and Supplementary Information (more rows can be added) |  |  |  |  | Abbreviations and Glossary (more rows can be added)
1 | www.university.ac.uk/researchculture/researchcultureworkshops/summary |  |  |  | PVC-RI | Pro-Vice Chancellor for Research & Innovation
2 | Using these spaces can help keep the main body of the action plan as concise as possible. |  |  |  | RCWG | Research Culture Working Group
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
This sheet gives a hypothetical response to a group of obligations under Environment and Culture > Awareness and engagement.
Tips and advice are shown alongside to highlight how to organise actions and success measures to deliver the most impact, as well as to demonstrate a transparent and compelling approach to reporting on progress and the original success measure.
For brevity, the remaining obligations have been omitted from this 'Tips' sheet.