## 2021-2023
HREiR Action plan (2021-2023 Backwards Action Plan)
Details
| Institution name: | De Montfort University |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | 17 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 2023-01-27 |  |  |  | Research staff |  | 12 | Defined as those on research-only fixed term contracts.
| Institutional context: | Research active staff are defined at DMU as any member of staff who is research active, and has been assigned a Research and Innovation Allowance (RIA) or a Researcher in Training (RIT) allocation (as of Spring 2021, the RIA has become the Staff Innovation Allowance (SIA), which includes three tracks -- research, teaching and knowledge exchange). Our focus, for the Concordat, will remain with those on the research track.) Where fixed-term contract research staff are identified, they will be supported with respect to career aspirations and redeployment discussions. |  |  |  | Postgraduate researchers
[6 empty] | Research and teaching staff |  | 617 | See institutional context for definition and description of T&R contracted staff.
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat. | A. The Concordat will be one of the key areas of focus for the Research Transformation Programme, which seeks to further embed a research culture in the university and support all research-active staff. The Concordat will be flagged as being the foundation for the Action Plan to develop and further enhance research capability in the university. B. The DMU Research external website, managed by RSD, features a section dedicated to the Concordat and the HR Excellence in Research award, which outlines our commitment to the Concordat. C. DMUConnect, the intranet for staff, is currently being redeveloped with plans to have a section dedicated to the Concordat. | No | A. 10/2021 B. 04/2021 C. 01/2022 | RSD, PVCER | The Concordat is referenced in strategy and policy documents, and particularly as part of the Research Transformation programme, in relation to DMU's research environment and culture. Increased awareness of Concordat and DMU's commitment to its values, as indicated by its presence highlighted in research induction events, relevant committee meetings and on relevant research communications and staff surveys. Guidance and training has Concordat embedded through all programmes. |  | The Concordat was discussed when the new Knowledge Creation strategy was created. It is at the heart of the strategy, with specific mention of Researcher Development as part of the priorities. The external website was updated with our actions and has had 530 unique visitors since its update in April 2021. Following the renewal of the HREiR, an internal bulletin was shared with all staff about the success and meaning of the award, noting the Researcher Development Concordat. Research Services DMUConnect pages were updated with relevant links to our external and internal pages mentioning the Concordat, together with a statement from the PVCR at the time on its significance to research culture and environment at DMU. The message was shared again in our internal DMU email that goes out to all staff. Completed on 15 April 2021. | 49.1% of academic staff have indicated that they have little to no knowledge of the Researcher Development Concordat in an internal survey on research environment and culture conducted in November 2022, emphasising the need for more awareness-raising around this Concordat. | Carried forward
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | A. Research time allocations are open, inclusive and equitable, and in line with the equality and diversity principles and ambitions of DMU. | Yes | January 2022 | RSD | Improving Outcomes Assessment on research time allocation exercises (e.g. the Research and Innovation Allowance, now Staff Innovation Allowance). |  | Following the impacts of COVID 19 and the move to a new block-teaching model, the decision was taken to roll over all Staff Innovation Allowances from 2020/21 to 2021/22. However, to better align with financial priorities, a new structure was temporarily set in place, with all allocations being Research, Innovation and Scholarship Awards (RISAs) at 160 hrs. | An Equality Impact Assessment was conducted on the potential impact, and those with higher allocations -- 480 and 320 -- were compensated such that all 480 award holders would automatically get a 7-week sabbatical to align with block teaching, and all those on 320s (which included a large number of Senior Lecturers, and staff from minoritised backgrounds) given the opportunity to apply for a block sabbatical (7 weeks). | Carried forward
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | A. Research institutes and centres, as well as ADRs/theme leads to embed review development and progress on quality of research environment and culture,including a move away from silo-working to more interdisciplinary working across faculties. | No | 2022-08-01 | RSD | Greater engagement in interdisciplinary events and activities, generating further outputs and outcomes. Bi-annual meetings of the REF Steering Committee finding more evidence of activities promoting research environment and culture, particularly at interdisciplinary level. Feedback at research events on research environment. |  | During the COVID pandemic, research seminars and talks were taken online. In 2020, The Doctoral College Lecture Series and special Faculty seminars were streamed using StreamYard - this included 10 talks in total. The online series of talks saw high numbers of engagement in 2020-2021 with more than 500 viewers. The Research Transformation Programme created five interdisciplinary themes for addressing global challenges -- creative and heritage industries; lifelong wellbeing; living in a digital age; net zero; and peace, equality and social justice. Following the launch of the themes in Spring 2022, a number of sandpits and events have supported interdisciplinary working, and membership of the themes cuts across all faculties. The launch provoked some very positive informal feedback on beginning to enjoy a sense of research community and collaboration again. Particularly significant is the engagement from early career researchers, who are able to avail of small pots of money to kickstart interdisciplinary activity via funding to the five themes. An internal survey on research culture and environment was conducted in November 2022. | While a buzz has been created with the launch of the interdisciplinary themes, with associated funding to pump-prime projects, the 2022 Research Environment and Culture Survey showed that academic staff feel the institution does not value efforts linked to research (eg 64.1% do not feel their contributions to external examining are valued; 60.1% do not feel efforts in policy and decision making are valued;). Staff were asked to describe DMU's research environment and culture in the survey as a way to collect open feedback - responses included "lacking", "undervalued", but also "promising", "potential". | Carried forward
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students.
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | A. RDT to continue to offer sessions such as 'Managing Research with Teaching Workloads' to researchers and create online resource on managing workloads with links to other initiatives (e.g. Employee Assistance Programme). B. RDT makes all development resources asynchronous and easily accessible for those who cannot attend live sessions. | No | A. January 2022 B. October 2021 C. January 2022 | RSD; POD | Increased provision and signposting of good mental health and wellbeing resources. |  | A. Managing Research with Teaching Workloads, which addresses workload and wellbeing challenges, was a new researcher development resource and ran over the last two years. Each session led by ADRs with input from ECR and MCRs to share their practice for managing time. The last 2 iterations (2020/21 and 2021/22) had 44 attendees (60% spaces filled). The feedback was positive and continues to be a regular part of our provision. B. In 2020, due to COVID, HR improved their signposting and developed online wellbeing resources, including a new external facing website to ensure easy access: https://www.dmu.ac.uk/coronavirus/health-wellbeing/index.aspx. The resource remains accessible and has had 5,456 unique visitors until 31 October 2022 since its inception in 9 April 2020 2. | While the training had positive feedback the 2022 Research Environment and Culture Survey had mixed results. While the majority of respondents (54%) indicated they had time in their workload for research, a follow-up question showed that staff on average conducted 10-15 hours of research on their own time. As such, the wellbeing strand continues to be one to watch, particularly as the University seeks to sign up to the Mental Health Charter. There is a specific stream of work on staff amongst the streams of Charter-related activity. | Carried forward
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | A. Mandatory training for managers includes Equality and Diversity Essentials and Understanding Unconscious Bias. B. Managers of researchers signposted to wellbeing and mental health provision and guidance, including the available training delivered by POD and the DMU Connect Sharepoint spaces. | No | A. October 2021 B. October 2021 | POD; RSD | 100% managers undertake this training. |  | Equality, Diversity Essentials (EDE) and Introduction to Bias (which includes unconscious bias) remains mandatory training for all staff at DMU to complete. Between January 2020 and November 2022, 60% of academic staff completed the EDE training; 50% had completed the Introduction to Bias. Of those who manage research staff (at the time, 12 individuals), 78% had completed the Equality and Diversity Essentials test; only 6% had completed the Bias training. Managers receive regular emails from POD which include reminders of mandatory training and how to access certain guidance. | Further uptake in training required. | Carried forward
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health.
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers.
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health.
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | POD to continue to offer training on wellbeing and managing stress; HR to continue to manage and enforce policies such as the Dignity at Work Policy. | No | 2022-01-01 | POD | Increased provision and signposting of good mental health and wellbeing resources. | The old template had only this as ECI3; as new template has two ECI3 so separated the action that more aligns to bullying/harassment to this space. | DMU's Dignity at Work Policy was renewed in September 2021. In November 2022, the VC sent out a central bulletin focusing on tackling misconduct and raising awareness to staff about key policies and where to access support. | Impact still to be realised as action to raise awareness was very recent and not been measured. | Carried forward
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying.
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion.
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | A. DMU currently offers Research Integrity and Ethics training to all research active staff, available as live or asynchronous iterations. This continues for 2021-2023 period. B. Additionally, DMU are looking to provide mandatory online research integrity training to all academic and research staff. | No | 2023-01-01 | RSD | A. Numbers of research-active staff attending training. B. Uptake of mandatory training. |  | During the 2020-2021 and 2021-2022 academic year, a workshop on Research Ethics and Integrity was delivered regularly (every two months) to academics at DMU. Regular recordings were made to ensure access for those who could not attend live iterations.28 staff attended the training. Feedback was positive (e.g. "Very informative and helpful session".). In 2021-2022, DMU procured the Epigeum modules on Research Ethics and Integrity. These were added to the Recommended Online Training Courses list on Blackboard and accessible by all staff members. As of 2022/23, reports of who has completed this training will be sent to the Faculty Research and Ethics Committees (FREC) for their information, with all FREC members to be mandated this training. | Despite the new resource and signposting (this is done weekly in our Researcher Development bulletin to staff), only 17 members of academic staff have thus far engaged with the online resources. | Carried forward
ECM3 | Ensure managers report and address incidents of poor research integrity.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct.
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | A. All relevant committee membership to include staff at different levels, including managers and those managed (early career researchers). | Yes | 2023-01-01 | RSD | All career stages (early, mid and senior) represented in committees like the University Research and Innovation Committee |  | DMU continues to have a governance structure where Faculty Research and Innovation Committees feed into University Research and Innovation Committee. Membership at the FRIC and University levels include ECR and MCR representation. Despite these actions, our 2022 Research Culture and Environment Survey, indicated that 53.3% of ECRs and 46.8% of MCRs did not feel they had opportunities to engage with decision-making. Overall, 46.4% of academics felt they did not have formal opportuities to engage with relevant organisational policy and decision making, while 24% neither agreed nor disagreed with respect to this statement. | Further consolidation is required. The Researcher Development Concordat Task and Finish Group discussed actions for upcoming committees to address membership and terms of reference to ensure researchers of all career stages are part of the committee structure. Institutional actions like the Green Paper consultations currently under way also provide opportunities for different voices to be heard. To be monitored. | Carried forward
ECM5 (ECI7) | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | A. Research Transformation Programme affording researchers opportunities to engage in creation of research strategy and allied discussions via consultation workshops and surveys. | No | October 2021; January 2023 | RSD | Engagement with workshops and survey to contribute to research strategy. |  | With a new leadership team taking office in January 2021, headed by a new Vice Chancellor, the institutional strategy was refreshed (the Empowering University strategy). As part of the development of that strategy, consultations were held on the shape of a new research and knowledge exchange strategy, with a consultation process that included opportunities for staff to engage via an online survey, or through focus group discussions on the key pillars of the strategy (Summer 2021). Following this process, the Knowledge Creation Strategy was launched (See Hyperlink 1). Further consultations on some key transformations (including the review of research into go out for consultation from mid December to 20 January 2023. | Analyses being conducted on whether there are differences in views across career stages. The full development of the strategy will be reviewed and key learning from the process noted going forward. | Carried forward
EM5 | Engage with opportunities to contribute to relevant policy development within their institution.
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution.
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community.
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices.
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | A. Researchers to continue to be invited to induction where this expectation is shared. Research Services plans to continue two research inductions events per academic year. | Yes | January 2022; January 2023 | RSD | Growth of new research active staff engaging with internal research activities. Increased engagement of 75% of new research active staff through attendance of research induction within 1 year of post or consultation with RDT via email/Teams meeting. |  | In October 2019, Research Services successfully launched a central induction programme that allowed new research-active staff to network and learn about research and related support at DMU. The plan to deliver two research inductions per academic year were derailed due to the change to online delivery. In 2019-2020 only 28% of new research-active staff participated in an induction. 2020-2021 saw the figure decrease to 24% - this was likely due to the challenges with teaching workloads and staff absences. Due to the low attendance, induction emails were introduced. Between Sept 2021-June 2022, 100% of new starters received an induction email from Research Services. Since June 2022, our induction process is under review with current plans to devolve the activity to faculties as part of the Empowering University strategy. This action will now be carried forward and reviewed in 3 years. | The Researcher Development Concordat Task and Finish Group discussed research inductions in great detail. The comments outlined a need to enhance the current staff induction to ensure research is fully embedded in that space while at the same time, faculty/local-level activities will be initiated to better integrate and welcome new researchers. The engagement at these events, and good practice examples will be noted. | Carried forward
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | A. Research leadership team to review criteria for SIA allocations, and align them to appraisal processes and promotion pathways at DMU | Yes | 2023-01-01 | RSD | Clear criteria for SIAs, and linking of objectives and outputs to appraisal processes; change evidenced by increased engagement from all research active staff for those on research track of SIA. |  | As mentioned above in ECI2, new criteria were set out for the RISA 160 with a straight rollover for all staff who had already had a SIA allocation in order to avoid creating more work at a time when staff were already heavily loaded with teaching and preparation for the block model of teaching. Recognition and reward have emerged as key areas that members of the Researcher Development Concordat Task and Finish Group think will create a supportive research environment and culture in the Research Environment and Culture survey conducted in November 2022. We will continue to monitor developments in this area, looking reward and recognition measures, and how research is monitored and linked in appraisal processes which currently tend to focus largely on teaching-related activities only. Feedback from staff on this subject included: rewarding peer-reviewing activities (DMU's Peer review college); more visibliity of current research endevours; research awards. | Staff appraisal processes continue to be under review. The Green Paper consultation on research includes consideration of criteria for Institute membership, recognition of all potential pathways (research, knowledge exchange, impact) and proposals for how research objectives might be assessed in appraisal processes. | carried forward
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers.
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding.
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder.
ER2 | Researchers understand their reporting obligations and responsibilities.
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | A. POD to continue to send out a regular 'Manager' communication to support line and project managers and signpost to relevant training; POD also continues to operate 'Elevensees-Manager Coffee meetings' as an open space for managers to discuss common challenges B. RDT training package for new Principal Investigators on research projects, including Concordat principles and responsibilities as a line manager. | No | 2022-09-01 | POD; RSD | Take-up by staff of new PI training. Response from CEDARS amongst group of new PIS. | With respect to CEDARs, the decision was made not to launch CEDARS in 2021 agaisnt a backdrop of significant due to institutional changes. It was also felt that the survey did not quite reflect the research-active population at DMU, which included very few research staff members. Instead an internal survey was launched in November 2022 to reflect on e environment and culture, as well as support for researchers, without specifically targeting PIs. | Manager communications have regularly been sent out to line managers at DMU; training for staff on line and project management have been halted during an internal review process. Research Services, led by the Researcher Development Team, developed two initiatives for researchers interested in becoming PIs and current PIs looking for support. The new PI training saw a 73% engagement rate with positive feedback as well as the launch of an informal community of practice for existing PIs to meet and discuss common challenges. These sessions are now a regular part of support for PIs and researchers who would like to be PIs. While CEDARs did not run, our own internal survey saw a 19.2% response rate. Of that popuation, most respondents identified as early career researcher or mid career researcher. | As staff training on line management is in development, details on the effectiveness of HRs endeavours to train line managers and heads of schools is not available. | Carried forward
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | A. MyAppraisal continues to operate as a system to manage appraisals, and includes section on people management. B. To support researchers contributing to the Researcher Development Programme, the RDT is working with line managers to ensure facilitators' time is recognised and is allocated to their workload. | Yes | 2022-09-01 | POD; RSD | Overt recognition of excellent line managers e.g. through Research Oscars. 80% of researchers contributing to Researcher Development Programme will have their time recognised as part of their workload allocation through discussions with line managers. |  | The appraisal system continues to operate during the period, though not as effectively, with most activities and management online during the pandemic, and with increased workloads and pressures on staff, especially with the move to block teaching in October 2022. No Research Oscars were promulgated during this period as institution-wide changes meant several initiatives had to be on hold. But the stress on reward and recognition in the research culture and environment survey will trigger actions to recognise and reward research, though not necessarily through Research Oscars. Researchers contributing to the Researcher Development Programme, largely from Health and Life Sciences as well as Business and Law have their time recognised through discussions with line managers. However, lack of data from other faculties who contribute to the programme suggests the 80% threshold was not reached. | Recognition of research and research-related activities still to be fully embedded in institutional structures. | Carried forward
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care.
EM4 | Managers actively engage in regular constructive performance management with their researchers.
ER3 | Researchers positively engage with performance management discussions and reviews with their managers.
Job security
The aim of this obligation is to improve the job security of researchers.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress.
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | A. Where research active staff are not on permanent contracts, it is recognised they may pursue careers across a wide range of employment sectors. As DMU maintains a collective agreement regarding the use of Fixed Term Contracts for academic staff that specifies non-permanent staff shall be treated no less favourably than permanent staff. B. As there are less than 11 non-permanent members of research active staff, the career support will be delivered a bespoke and 1-2-1 level and managed through their line manager. C. For research-active academic staff, continue to provide institute- and faculty-level support to build their capabilities in research and related areas, particualrly through peer learning. | Yes | March 2022 | Research Services | Engagement levels in professional development through University and external programmes, captured for instance via Next Generation Researcher programme. Increase engagement of Next Generation Researchers from 20% of cohort attending over 3 professional development sessions in the programme to 40% of cohort engagement. |  | Over the last two years, research staff have not been greater than 18 individuals. As per our policies, research staff on fixed term contracts had access to the same training as T&R researchers. This resulted in 37 bookings across 2021-2022; records to this level were not kept in 2020-2021 as we were in the process of upgrading our booking systems. While 1-2-1 bespoke offering is available to research staff, only 1 has made an appointment with the researcher development manager. Further work is needed to ensure research staff on FT contracts are aware of these opportunities to meet with support staff and engage with professional development. There were three Next Generation cohorts (117 members of T&R staff) supported through the last two years - noting that cohort 1 merged with cohort 2 due to the pandemic. Feedback from research-active staff attending professional development opportunities has been positive. Particular positive feedback was received following networking training delivered in 2020-2021 and then again in 2021-2022 by an external facilitator demonstrating the value of these sessions. | Engagement increased from 25% (2019-2020 cohort) to 73% (2020-2021) but decreased to 41% (2021-2022 cohort). The decrease in 2021-2022 has been attributed to prioritisation of Education 2030 (a University wide teaching initiative that took up development time for the cohort members). | Carried forward
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | A. Researcher Development Manager to monitor attendance and report on engagement of researchers in career related sessions. | Yes | Sept 2020 and Sept 2021 | RSD | Attendance and engagement data from 2019-2020 is incomplete but from the Researcher Development Programme alone, 5% researchers engaged in professional development activities. This leaves out professional development data from POD. Increase engagement to 25% by 21 September 2022 and add to the annual report on researcher development activities undertaken by staff to be produced each academic year |  | Reporting on researcher development was difficult in 2020-2021 due to record-keeping largely being done manually. In 2021, ResJourney was launched for research degree students which also included a research training booking system which was opened up to all research active staff. As such since 2021, reporting and data capture of staff engagement with researcher development has greatly improved. Engagement of staff on the researcher development programme has been very positive with many engaging in a range of sessions (e.g. grant development; research skills development; and supervising students). The booking system and centralisation of many events has supported this positive output. | In 2020-2021, 270 academics engaged with professional development activities (43% increase). This increased to 310 (51%) academics in 2021-2022. Note that these percentages are calculated based on the number of academics identified as benefiting the 2021-2023 Concordat (617 research-active academics). | No further action - success measures were met and is now part of business as usual with plans to review again in 3 years.
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development.
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year.
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | see above (EI4) | No | 2022-09-01 | POD; RSD | see above (EI4) |  | Professional development opportunities available to managers of researchers are delivered by People and Organisational Development. The PI training sessions had elements focused on how to lead research teams, including conversations about career developments. | As above engagement with PI training sessions was quite high (73%) and is now part of the regular training for researchers and current PIS. Support for managers from POD is to be reviewed alongside other HR/staff training as part of a wider reviewer of staff development. | No further action - part of the success measures were met and obligation is being deprioritised.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews.
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually.
PCDR4 | Researchers positively engage in career development reviews with their managers.
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | A. RDT to enrich the Researcher Development Programme with career management support and enterprise opportunities. Asychronous resources to be developed from live sessions. | No | 2021-09-01 | RSD | Take up of career development sessions, including enterprise sessions and broader skills sessions (e.g. networking effectively). |  | Between 2021-2023, regular sessions have been included in the Researcher Development programme for research staff, including those focused on enterprise. Sessions such as 'Garage to Global - an Entrepreneur's Journey' and 'Introduction to Enterprise and Working with Businesses' demonstrate our commitment to raise awareness of other research careers and research opportunities. Networking training was organised in 2020-2021 and 2021-2022. | Engagement with enterprise and innovation sessions has been quite low resulting in sessions being cancelled or rearranged. Networking training saw better engagement with (online) had 18 academics participate; the second and third iteration in 2021-2022 had a total of 33 attendees. | Carried forward
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications.
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | A. RDT to develop a package of structured support designed to support those looking to scale up their research careers and begin to develop bids and pursue research outputs greater than before. B. A session on 'What does research leadership look like' is to be developed for researchers to help raise increased awareness of what a research leader looks like and to encourage researchers to strive to be leaders in their fields. C. Develop the Research and Scholarship Scheme's commitment to develop Research Assistant and Teaching Assistant posts which allow researchers the opportunity to grow their leadership and mentoring skills. | No | A. Sept- 2021 B. Sept- 2021 C. Sept- 2022 | RSD | Review feedback on the efficacy of package of support for staff, including the leadership workshops. Measure the attendance of these workshops and embed Concordat information to align with ECI1. Capture and evaluate outcomes for both students and staff on the Research and Scholarship Scheme on first cohort |  | A. Due to the pandemic, and staff loads emerging from new ways of teaching, and preparations for moving to a block teaching model from October 2022, there has not been sustained activity in relation to this action. The Researcher Development Programme has incorporated sessions supporting grant writing, with a focus on different funders, which has been complemented by faculty drop-in sessions from the Research Development Officers to provide one-to-one support in developing grant applications. Also emerging over this period is a far more structured Peer Review College to provide feedback on grant applications. The end of year report for 2021/22 shows that all grant applications submitted (189) in 2021-22 underwent at least one peer review. The process is continuing over 2022/23. B. A significant development in this context is the initiation of a Principal Investigator group that meets regularly to provide peer support for researchers new to research leadership on grants. The Future Research Leaders programme continued apace over this period, with up to 12 recruits per year, with ECR participation. Again, further development of a programme of activity to support research leadership has been stymied on account of Covid-related pressures. C. The Research and Scholarship Scheme supported several staff with Research (13) and Teaching Assistants (7). It further included a research leave scheme, with two members per faculty availing of this in 2021/22. The scheme has been temporarily suspended in 2022/23 given the initiation of block teaching and an ongoing review of the research strategy and priorities. However, RA support continues to be offered via the themes through 2021/22 and 2022/23. | The peer review scheme and PI support have increased confidence and quality of applications. To further support and consolidate ECRs and MCRs, a new leadership programme is to be rolled out in 2023/24. Called Advancing your Research Career (ARC) the programme will have cohorts sizes of 20 in each category, and they will feed into the Future Research Leaders programme, which will be positioned to attract more senior researches on the cusp of professorship and research leadership. | Carried forward
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours.
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development.
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | A. Workshops available to postgraduate researchers that look at the employment sector to be made open to research active staff. | Yes | 2021-09-01 | RSD | Provision of information on a range of employment sectors and opportunities within those sectors; measured via the uptake of these resources. |  | Seminars for postgraduate researchers have taken place to highlight alternative career paths and how researchers within academic settings can engage with other employment sectors. The plan for these to be opened up to research staff did not come to fruition as PGR Careers Advisors remit does not allow expansion to include this audience. However, professional development activities for research staff did take place (organised by Research Services). This included networking, research sandpit, enterprise and knowledge exchange events. | Research staff have opportunities to engage with events that explore alternative career paths, including enterprise activities and knowledge exchange pathways. Networking and other staff development opportunities are available to them. | No further action - support for research staff and raising awareness of alternative career paths is addressed in PCDI3.
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments.
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments.
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | https://www.dmu.ac.uk/empowering-university/knowledge-creation.aspx |  |  |  | ADR | Associate Deans of Research
2 |  |  |  |  | APVCR | Associate Pro Vice-Chancellor for Research
3 |  |  |  |  | DMU | De Monfort University
4 |  |  |  |  | EDE | Equality Diversity Essentials
5 |  |  |  |  | EDI | Equality, Diversity and Inclusion
6 |  |  |  |  | HR | Human Resources
7 |  |  |  |  | PI | Principal Investigator
8 |  |  |  |  | POD | People and Organisational Development
9 |  |  |  |  | PVCR | Pro Vice-Chancellor for Research
10 |  |  |  |  | RSD | Research Services Directorate
11 |  |  |  |  | TDs | Theme Directors
12
13
14
15
16
17
18
19
20